## from 27 Jan to 4 Feb 2022
ICU- PO`s Weekly Report
Reporting period from:7 Feb to 11 Feb 2022
Completed
Ser.# | P.O # ..AWB/BL # | RFQ Number | T.O. Number | Description | From | Package | QTY | Total Weight | Consignee | Qty / Road (Trucks) | POD | Mission Region Destination | Date Completed | Remark
TOTAL | [6 empty] | 0 | 0 |  | 0
Tasks Planned for the Next Reporting Period: 14 Feb to 18 Feb 2022
Ser.# | P.O # ..AWB/BL # | RFQ Number | T.O. Number | Description | From | Package | QTY | Total Weight | Consignee | Qty / Road (Trucks) | POD | Mission Region Destination | Date Planned | Remark
1 | 2200178405 | MOV053 | 1551 | Ballistic Helmets | China | Container 20 ft | 1 | 413 | Supply | 1 | Dakar | Bamako | TBC | Under Customs process
TOTAL | [6 empty] | 1 | 413 |  | 1
Other Ongoing Plans and Projects (next 30 Days) SEA shipment
Ser.# | P.O # ..AWB/BL # | RFQ Number | T.O. Number | Description | From | Package | QTY | Total Weight | Consignee | Qty / Road (Trucks) | POD | Mission Region Destination | Date Planned | Remark
1 | 2200177529 | MOV053 | N/A | Personal Protective Equipment | USA | Pallet | 1 | 311 | Aviation | 1 | Dakar | Bamako | 2023-05-20 | In Dakar waiting ECOWAS sanction end
2 | 2200192299 | MOV063 | N/A | Battery Fuse, Batteries | China | Container 20 ft | 14 | 84200 | FTS | 7 | Dakar | Bamako | 2023-05-14 | In Dakar waiting ECOWAS sanction end
3 | 2200205679 | MOV079 | N/A | Modular Power Pack Unit | Italy | Container 20 ft | 6 | 19980 | Eng | 3 | Dakar | Bamako | 2023-05-19 | In 2HL warehouse waiting ECOWAS sanction end
4 | 2200195272 | MOV084 | N/A | Air Conditioner and Spare Parts | China | Container 20 ft | 6 | 84200 | Eng | 3 | Nouakchott | Bamako | 2023-05-05 | Port formalities in process
5 | 2200195275 | MOV084 | N/A | Air Conditioner and Spare Parts | China | Container 20 ft | 6 | 18526 | Eng | 3 | Nouakchott | Bamako | 2023-06-02 | Port formalities in process
6 | 2200195273 | MOV084 | N/A | Air Conditioner and Spare Parts | China | Container 20 ft | 4 | 12953 | Eng | 2 | Nouakchott | Bamako | 2023-06-10 | Port formalities in process
7 | 2200195267 | MOV085 | N/A | Air Conditioner and Spare Parts | China | Container 20 ft | 18 | 57643 | N/A | 9 | Cotonou | Gao | 2023-05-13 | ETA Cotonou 13 Feb
8 | 2200167828 | MOV092 | 121 | Furnitures and accessories | Italy | Container 40 ft | 1 | 10552 | Supply | 1 | Dakar | Bamako | 2023-02-13 | ETA 13 Feb 2022
9 | 2200199361 | N/A | N/A | Spare Parts | Canada | Container 20 ft | 1 | 603 | Eng | 1 | Dakar | Bamako | 2023-06-02 | Currently at Dakar
10 | 2200206347 | N/A | 70 | Tyres | UAE | Container 20 ft | 1 | 2760 | Tyres | 1 | Dakar | Bamako | 2023-06-05 | Currently at Dakar
TOTAL | [6 empty] | 58 | 291728 |  | 31